## Summary
Cardstack — build status
Generated 2026-08-03 from the working tree at commit 0303abf. Counts are live formulas over the other tabs.
Area | Done | Partial | Open | Descoped | Total | % Done
Backend
Frontend (Studio)
Widgets
Milestones
Design refs
Open work
TOTAL
How to read this
Done | Built and verified — tests, a demo script, or driven in the browser this session.
Partial | Something real ships, but the design reference or milestone is not fully met. Notes say which half.
Open | Not built.
Descoped | Deliberately parked. Excluded from the % Done denominator, since it is not outstanding work.
Status column | A dropdown on every detail tab — edit it as work lands and the Summary counts follow.
Evidence | Where to look in the repo. '-' means nothing exists yet.
Caveat | Status reflects code presence + this session's verification, not a fresh QA pass of every surface.

## Backend
Backend — MCP server, adapters, store, auth
38 items · status column is a dropdown — edit it as work lands
Area | Item | Status | Notes | Evidence (file / path)
MCP tool — read | crm_list_objects | Done | Lists exposed objects for the workspace. | apps/mcp-server/src/server.ts
MCP tool — read | crm_search | Done | Golden Path 1. Returns the results-table widget. | apps/mcp-server/src/server.ts
MCP tool — read | crm_get_record | Done | The record card. Denylist-filtered server-side. | apps/mcp-server/src/server.ts
MCP tool — read | crm_get_related | Done | Related lists + drill-through. | apps/mcp-server/src/server.ts
MCP tool — read | crm_list_view | Done | M2.5 saved views, alias routing, ambiguous-ask picker. | apps/mcp-server/src/views.ts
MCP tool — read | crm_lookup_search | Done | Typeahead for reference fields in edit mode. | apps/mcp-server/src/server.ts
MCP tool — read | crm_aggregate | Done | Exact server-side totals, optionally grouped. | apps/mcp-server/src/server.ts
MCP tool — read | crm_home | Done | M4 home card: list tiles, recents, follow-ups. | apps/mcp-server/src/server.ts
MCP tool — write | crm_preview_update | Done | Server-computed confirmation diff + signed confirm token. Writes nothing. | apps/mcp-server/src/server.ts
MCP tool — write | crm_update_record | Done | Verifies the confirm token before writing; bad token aborts. | apps/mcp-server/src/server.ts
MCP tool — write | crm_preview_complete_task | Done | Mints the token behind the home card's inline check-off confirm. | apps/mcp-server/src/server.ts
MCP tool — write | crm_complete_task | Done | Token-verified; logs widget vs model provenance. | apps/mcp-server/src/server.ts
MCP tool — write | crm_create_record | Descoped | DESCOPED 2026-08-03 (your call): not needed right now. Exists and works; logs as model-initiated since it has no confirm surface. In-widget create (10b) parked with it. | apps/mcp-server/src/server.ts
MCP tool — flows | crm_flow_start | Done | Native rung: interprets the flow definition and renders in chat. | apps/mcp-server/src/server.ts
MCP tool — flows | crm_flow_continue | Done | Screens, branching, back, confirm-write pause. | packages/core/src/flow-interview.ts
MCP tool — flows | crm_flow_cancel | Done | No longer requires flowApiName (UX review 18). | apps/mcp-server/src/server.ts
MCP tool — flows | crm_quick_action_start | Done | Salesforce quick actions: describe -> render -> confirm -> execute. | apps/mcp-server/src/server.ts
Flow interpreter | Native rendering in chat | Done | Full element coverage; static analysis picks native vs handoff. | packages/core/src/flow-analysis.ts
Flow interpreter | Silent degrade to handoff | Open | RISK: an unsupported object/element degrades quietly mid-run (hit 'Unknown object: Task' in test). No admin-facing signal when a flow stops being native in the live org. | apps/mcp-server/src/server.ts
Adapters | Mock (HubSpot-shaped portal) | Done | Fixtures for tests + demos. | packages/crm-adapters/src/mock
Adapters | HubSpot | Done | M1.5. | packages/crm-adapters/src/hubspot
Adapters | Salesforce | Done | M2+. Flows, quick actions, list views, recents. | packages/crm-adapters/src/salesforce
Config store | File-backed store | Done | Default local; shared with Studio. | packages/config-store/src/file-store.ts
Config store | Postgres store | Done | Behind DATABASE_URL for Railway. | packages/config-store/src/postgres-store.ts
Config store | Draft / publish / rollback | Done | Revisioned; publish diff; rollback API + UI. | packages/config-store/src/diff.ts
Config store | Durable audit log | Done | File JSONL + Postgres JSONB; survives redeploys. | packages/config-store/src/audit-log.ts
Auth | Cardstack accounts (Salesforce OAuth) | Done | A workspace IS a Salesforce org; first signer creates it. | docs/accounts-and-workspaces.md
Auth | Per-user MCP auth (OAuth 2.1) | Done | Salesforce as identity provider; bearer token on /mcp. | apps/mcp-server/src/oauth-provider.ts
Auth | Session-cookie identity in Studio | Done | x-cardstack-* headers no longer trusted. | packages/config-store/src/identity.ts
Auth | Multi-workspace tenancy | Done | Cross-tenant isolation asserted in tests. | packages/config-store/src/tenant-isolation.test.ts
Security | Denylist enforced server-side | Done | Hard rule 2: the widget only ever receives permitted fields. | packages/core/src/filtering.ts
Security | Required fields can't be cleared | Done | Layout-marked and CRM-required both enforced on write. | apps/mcp-server/src/server.ts
Security | CRM tokens encrypted at rest | Done | AES-256-GCM envelope; plaintext passthrough only with no key. | packages/config-store/src/crypto.ts
Security | Confirm tokens (write provenance) | Done | HMAC bound to tenant/object/record/actor/patch-hash; never degrades to unsigned. | apps/mcp-server/src/confirm-token.ts
Security | One signing floor for all write paths | Done | Interview + quick-action state share the confirm-token signer. Fixed unsigned passthrough when no key set. | apps/mcp-server/src/confirm-token.ts
Ops | /healthz reports commit + boot time | Done |  | apps/mcp-server/src/main.ts
Ops | Railway deploy (2 services + Postgres) | Done | MCP server + Studio, both live. | -
Ops | pnpm lint runs zero tasks | Open | No lint task is defined in any package, so 'pnpm lint' silently passes without linting anything. | turbo.json

## Frontend (Studio)
Frontend — Cardstack Studio (Next.js admin UI)
24 items · status column is a dropdown — edit it as work lands
Area | Item | Status | Notes | Evidence (file / path)
Studio shell | Navigation shell (12b) | Done | Cards / Workspace nav, per-object sub-nav. | apps/studio/components
Studio shell | Sign-in page | Done | Salesforce OAuth. | apps/studio/app/login
Studio page | Overview / home (6b) | Done | Per-object cards, metadata-gap nudges, publish history. | apps/studio/app/page.tsx
Studio page | Card design / layout builder (2a) | Done | Palette + dnd canvas + REAL-widget live preview. The demo moment. | apps/studio/app/objects/[object]/layouts
Studio page | Lists & views (5a) | Done | Exposure config, aliases, object-aware placeholders. | apps/studio/app/objects/[object]/lists
Studio page | Write access / permissions (2e) | Done | Confirmation locked ON, stated as product stance. | apps/studio/app/objects/[object]/permissions
Studio page | Assignment (2f-2i) | Partial | v1 teaching state only: one default layout. Audience matrix + View-as not built. | apps/studio/app/objects/[object]/assignment
Studio page | Home card builder (8a) | Done | Block toggles with REAL HomeCard preview; publish bumps revision. | apps/studio/app/home-card
Studio page | Flows admin | Done | Exposes org flows, assigns to cards, auto-maps variables. | apps/studio/app/flows
Studio page | Connections (2c) | Done | Admin + per-user OAuth lanes, trust framing, scope coverage. | apps/studio/app/connections
Studio page | Write activity / audit | Done | Now includes the Confirmation column + CSV provenance columns. | apps/studio/app/audit
Studio page | Custom screens (11a) | Partial | Editor scaffolded but carries 'Preview - not yet live'. M6 runtime not built. | apps/studio/app/custom-screens
Builder feature | Publish diff modal (2b) | Done | Honest copy, Escape-closes, focus-trapped. | apps/studio/components/builder
Builder feature | Versions / rollback UI | Done | Rows name their target revision. | apps/studio/app/api/layout/[object]/rollback
Builder feature | Layout auto-generation (2c/3c) | Done | Reads describe, ranks high-signal fields, groups into sections. | apps/studio/lib/starter-layout.ts
Builder feature | Field palette ranking | Done | Signal-ranked; address/system collapsed; title/subtitle filtered. | apps/studio/components/builder
Builder feature | Actions editor (3a) | Done | Action components with render policy + inputs mapping. | apps/studio/components/builder
Builder feature | Related-list picker (3b) | Partial | Deduped, grouped, filterable. Full 3b relationship metadata + per-list settings still open. | apps/studio/components/builder
Builder feature | Add-action picker (10c) | Partial | Platform flows hidden by default; writes-summary per flow not surfaced. | apps/studio/components/builder
Builder feature | Requirements pass-through (3d) | Partial | Required chips render and are enforced on write; full 3d pass-through open. | apps/studio/components/builder
Builder feature | Audience picker (3e) | Open | Not built. Blocks the audience/role-based layout story (V1). | -
Builder feature | Live preview fidelity | Done | True-width render + zoom-to-fit; 380 toggle engages the mobile layout. | apps/studio/components/builder/preview.tsx
Builder feature | Metadata-gap CTA | Done | 'Fix in <CRM>' deep link rather than a dead-end callout. | apps/studio/components/builder
Studio a11y | Publish modal Escape + focus trap | Done | UX review 11, Studio half. | apps/studio/components/builder

## Widgets
Widgets — the four MCP App bundles reps actually see
21 items · status column is a dropdown — edit it as work lands
Area | Item | Status | Notes | Evidence (file / path)
Record card | Read-only render (1a) | Done | Sections, header slots, badges, field tooltips. | packages/widgets/src/record-card
Record card | Edit mode / dirty state (1b) | Done | Explicit state machine; at-rest mark on editable fields. | packages/widgets/src/record-card/edit-machine.ts
Record card | Confirmation diff (1c) | Done | NOW SERVER-COMPUTED via crm_preview_update; label-based, never color-alone. | packages/widgets/src/record-card/card.tsx
Record card | Write receipt (4c) | Done | Per-field outcomes; re-fetched display values. | packages/widgets/src/record-card/write-states.tsx
Record card | Partial failure + Edit & retry (1e) | Done | Verbatim CRM validation messages per field. | packages/widgets/src/record-card/write-states.tsx
Record card | Drill-through | Done | Clickable refs and related rows open in-card. | packages/widgets/src/record-card/card.tsx
Record card | View in CRM deep link | Done |  | packages/widgets/src/record-card/card.tsx
Record card | In-widget create form (10b) | Descoped | Parked with crm_create_record. Posts a chat followup instead. | packages/widgets/src/record-card/card.tsx
Results table | Table + drill-in (1f) | Done | Rows open the record card inside the table widget. | packages/widgets/src/results-table
Home card | Tiles / recents / follow-ups (7a) | Done | Live counts; real LastViewedDate; no fabricated timestamps. | packages/widgets/src/home-card
Home card | Task check-off | Done | Inline confirm now backed by a server-minted token. | packages/widgets/src/home-card/card.tsx
Flow run | Native screen rendering (10a) | Done | All element kinds; back; confirm-write pause. | packages/widgets/src/flow-run
Flow run | 380px breakpoint | Done | Was the only widget without one. | packages/widgets/src/flow-run/flow-run.css
Cross-widget | Dark mode / host tokens (1d) | Done |  | packages/widgets/src/shared/theme.css
Cross-widget | Mobile 380 (1g) | Done | Container queries, not media queries, so Studio preview matches. | packages/widgets/src/shared
Cross-widget | 'as of HH:MM' chip | Done | Staleness down-payment from provenance.fetchedAt. | packages/widgets/src/shared/components.tsx
Cross-widget | Stale-card strip + Refresh (1e) | Open | Full 1e treatment not built. An old card still looks live apart from the as-of chip. | -
Cross-widget | Re-auth state | Done | Keeps in-progress edits mounted. | packages/widgets/src/record-card
Cross-widget | aria-live on write transitions | Open | Verified ZERO aria-live in packages/widgets/src. confirming->receipt/partial is silent to screen readers. | -
Cross-widget | Focus management on view swaps | Open | Verified ZERO .focus() calls. Focus dies on unmounted elements after drill-in/Back. | -
Cross-widget | combobox aria-activedescendant | Open | UX review 11, widget half. | -

## Milestones
Milestones — PLAN.md M0–M7
12 items · status column is a dropdown — edit it as work lands
Area | Item | Status | Notes | Evidence (file / path)
Milestone | M0 - hello-world MCP App round trip | Done | Widget renders, widget->tool round trip, updateModelContext. | PLAN.md
Milestone | M1 - read-only card + results table | Done | Golden Path 1. pnpm demo:m1 passes. | apps/mcp-server/scripts/demo-m1.ts
Milestone | M2 - writes, confirm, receipt, audit | Done | Golden Path 2. pnpm demo:m2 passes (now walks the token path). | apps/mcp-server/scripts/demo-m2.ts
Milestone | M2.5 - saved views | Done | Golden Path 2.5. pnpm demo:m2.5 passes. | apps/mcp-server/scripts/demo-m25.ts
Milestone | M3 - Studio core | Done | Golden Path 3. pnpm demo:m3 passes. | apps/mcp-server/scripts/demo-m3.ts
Milestone | M4 - home card + builder + tasks | Done | pnpm demo:m4 passes. | apps/mcp-server/scripts/demo-m4.ts
Milestone | M5 - flows | Done | Native interpreter, flows admin, quick actions. No demo script yet. | packages/core/src/flow-interview.ts
Milestone | M6 - custom screen SDK | Partial | Editor scaffolded; runtime not live. Largest net-new subsystem remaining. | apps/studio/components/custom-screens-editor.tsx
Milestone | M7 - hardening / registry / evals | Open | Not started. Confirmation provenance was the first M7-adjacent piece. | -
Beyond plan | Cardstack accounts + multi-workspace | Done | Not in the original milestone map; shipped ahead of it. | docs/accounts-and-workspaces.md
Beyond plan | Per-user MCP OAuth | Done | Ditto. | apps/mcp-server/src/oauth-provider.ts
Beyond plan | Local dev against a real SF org | Done | seed:salesforce + dev:sf using the sf CLI token in memory only. | CLAUDE.md

## Design refs
Design references — /design README ids
34 items · status column is a dropdown — edit it as work lands
Area | Item | Status | Notes | Evidence (file / path)
Design ref | 1a Record card, read-only | Done |  | design/README.md
Design ref | 1b Edit mode / dirty state | Done |  | design/README.md
Design ref | 1c Confirmation diff (signing moment) | Done |  | design/README.md
Design ref | 1d Dark mode | Done |  | design/README.md
Design ref | 1e Edge states | Partial | Loading/empty/error done; stale strip open. | design/README.md
Design ref | 1f Results table | Done |  | design/README.md
Design ref | 1g Mobile 380 | Done |  | design/README.md
Design ref | 1h Stress test | Done |  | design/README.md
Design ref | 2a Layout builder | Done |  | design/README.md
Design ref | 2b Publish flow | Done |  | design/README.md
Design ref | 2c Connect & onboarding | Done |  | design/README.md
Design ref | 2e Permissions | Done |  | design/README.md
Design ref | 2f-2i Assignment matrix / View-as | Partial | Teaching state only. | design/README.md
Design ref | 3a Actions editor | Done |  | design/README.md
Design ref | 3b Related list picker | Partial | Dedupe/group/filter shipped; relationship metadata open. | design/README.md
Design ref | 3c Object picker | Done |  | design/README.md
Design ref | 3d Requirements pass-through | Partial | Required chips + server enforcement; full pass-through open. | design/README.md
Design ref | 3e Audience picker | Open |  | design/README.md
Design ref | 3f Rules in the widget | Partial | Verbatim CRM validation shipped; rules read-through open. | design/README.md
Design ref | 4c Write receipt | Done |  | design/README.md
Design ref | 5a List views page | Done |  | design/README.md
Design ref | 5b List resolution | Done |  | design/README.md
Design ref | 6a IA map | Done |  | design/README.md
Design ref | 6b Studio home | Done |  | design/README.md
Design ref | 7a Home card | Done |  | design/README.md
Design ref | 8a Home card builder | Done |  | design/README.md
Design ref | 9a Add-block menu | Done |  | design/README.md
Design ref | 10a Screen flow mid-run | Done |  | design/README.md
Design ref | 10b Home actions + create form | Descoped | Descoped with crm_create_record. | design/README.md
Design ref | 10c Add action picker | Partial | Platform flows hidden; writes-summary open. | design/README.md
Design ref | 11a Custom screen SDK editor | Partial | Editor only - 'Preview, not yet live'. | design/README.md
Design ref | 11c Embedded screen | Open |  | design/README.md
Design ref | 12a Record card w/ custom section | Open |  | design/README.md
Design ref | 12b Studio navigation shell | Done |  | design/README.md

## Open work
Open work — what's left, ranked by area
12 items · status column is a dropdown — edit it as work lands
Area | Item | Status | Notes | Evidence (file / path)
Accessibility | Widget a11y pass | Open | aria-live for write states, focus management on drill-in/Back, aria-activedescendant. Design commits to a full keyboard path; the widget half is at zero. | packages/widgets/src
Trust | Stale-card strip + Refresh (1e) | Open | Biggest remaining trust gap for a card living in a chat scrollback. | -
Studio | Audience picker (3e) + assignment matrix (2f-2i) + View-as | Open | Blocks role-based layouts (roadmap V1). | -
Studio | Custom screen SDK runtime (M6, 11a) | Open | Editor exists; guardrails, versioning and the live runtime do not. | -
Studio | Embedded screen (11c) / custom card section (12a) | Open | Depend on M6. | -
Flows | Surface silent handoff degrades | Open | MY FINDING: a flow can stop rendering natively mid-run with no admin-facing signal. | apps/mcp-server/src/server.ts
Polish | Activity/recents hygiene (13) | Open | Relative times; due-date styled as 'due X' not a timeline stamp. | -
Polish | Shared governance vocabulary (14) | Open | Layouts publish; lists and flows go live immediately. Three mental models, no shared badge. | -
Polish | Zero-count home tiles (15) | Open | Empty lists take premium home-card slots. | -
Tooling | pnpm lint defines no tasks | Open | MY FINDING: lint silently passes without linting. | turbo.json
Docs | CLAUDE.md 'Current phase' is stale | Open | Still describes M4 as current; M5, flows, quick actions, OAuth and accounts all shipped after. | CLAUDE.md
Descoped | crm_create_record confirm surface | Descoped | Your call 2026-08-03: not needed right now. Revisit with in-widget create (10b) if creation becomes a rep-facing need. | -